## List
TASK | START DATE | DURATION
Requirement Gathering | 26/12/2017 | 10
Documentation | 5/1/2018 | 10
Wireframe | 15/1/2018 | 7
UI Design | 22/1/2018 | 4
ER Design | 26/1/2018 | 3
Database Design | 29/1/2018 | 5
User and Admin Frontend Design | 2018-03-02 | 25
User and Admin Backend Design | 28/2/2018 | 25
Testing | 26/3/2018 | 10